## Slide 1: Masked Face Recognition
Ahmad jawabreh
Zaid Mohtaseb
Ferhat bal

## Slide 2: Activity cost estimate
Critical Assumptions and Constraints
1- Because of the war in Europe and the problems of the supply chain from China and many countries of the world, the prices of silicon chips have been rising for more than a year, we assumed that the prices would remain the same until we order them.
2- The dealer of the hardware parts is baying the parts from China with US dollar any they are selling it with Turkish lira, so if the exchange rate changed the price also will be changed, so we assumed the exchange rate will stay on 1USD = 14.75TL.
3- We assumed that we will not pay for any external services such as a programmers or electronic and electrical engineer, which the cost estimation table contains only the hardware parts.

## Slide 3: Cont.
WBS Item Number | WBS Item |  | Resource Type 1 |  | Total
1. | Hardware Parts | 32/1 | - | - | 1885 TL
1.1. | RFID parts | 3/1 | - | - | 1136 TL
1.1.1. | RFID | 1/1 | 31 TL/1H | 31TL | 31 TL
1.1.2. | LED’s | 2/1 | 3.5 TL/1H | 3.5 TL | 7 TL
1.1.3. | Alphanumeric LCD | 1/1 | 219 TL/1H | 219 TL | 219 TL
1.2. | Masked face recognition parts | 2/1 | - | - | 376.5 TL
1.2.1 | Camera | 1/1 | 157.5 TL/1H | 157.5 TL | 157.5 TL
1.2.2 | LCD screen | 1/1 | 219 TL/1H | 219 TL | 219 TL
1.3. | Sensors part’s | 4/1 | - | - | 137.9 TL
1.3.1 | Distance sensor | 1/1 | 31.5 TL/1H | 31.5 TL | 31.5 TL
1.3.2 | Gas sensor | 1/1 | 28.4 TL/1H | 28.4 TL | 28.4 TL
Cost estimate

## Slide 4: Cont.
WBS Item Number | WBS Item |  | Resource Type 1 |  | Total
1.3.3 | Flame sensor | 1/1 | 35 TL/1H | 35 TL | 35 TL
1.3.4 | Speaker | 1/1 | 43 TL/1H | 43 TL | 43 TL
1.4. | Network parts | 1/1 | - | - | 107.5 TL
1.4.1 | Ethernet port | 1/1 | 107.5 TL/1H | 107.5 TL | 107.5 TL
1.5. | Power and electricity parts | 2/1 | - | - | 43.47 TL
1.5.1 | Battery | 1/1 | 9.45 TL/1H | 9.45 TL | 9.45 TL
1.5.2 | Power Cable | 1/1 | 34.2 TL/1H | 34.2 TL | 34.2 TL
2. | Coding | 0 | 0 | 0 | 0
3. | Database creation | 0 | 0 | 0 | 0
4. | Smart contract development | 0 | 0 | 0 | 0
5. | Testing | 0 | 0 | 0 | 0

## Slide 5: Business case
Current Situation and Problem/Opportunity Statement
    Current Situation: For using the system for public control there is a huge gap in the current systems, Because this systems are here to control the people which means decreased the number of crimes.
    Gap: The perpetrators of crimes can easily cover his face it means the algorithm of the system in broken.
    Solution: Using god eye technology with a stable and accurate masked face recognition system will led to reducing crimes to the lowest levels.

## Slide 6: Cont.
Target Benefits
  Masked Face recognition system for locking and unlocking the door.
  Masked Face recognition system as part of god eye project for public control.
  Masked Face recognition system can be used for face passport (Biometric passport).
  Solving the problem of inability to recognize masked faces which means solving of huge crimes.

## Slide 7: Cont.
Outputs:
Masked Face Recognition System.
Alternative authentication method, RFID system.
Blockchain connection to data transfer and validation.

## Slide 8: Communication Matrix
Stakeholder | Type | Communication Medium | Frequency | Responsible Party
Ahmad Jawabreh | Work progress report | Email (Protonmail) | Every Day | Zaid Mohtaseb
Ahmad Jawabreh | Software and code status | GitHub | Day after day | Zaid Mohtaseb
Zaid Mohtaseb | Work progress report | Email (Protonmail) | Every Day | Ahmad Jawabreh
Zaid Mohtaseb | Hardware connection maps and documentation | GitHub | Day after day | Ahmad Jawabreh
Ahmad Jawabreh | Work progress report | Email (Protonmail) | Every Day | Ferhat Bal
Zaid Mohtaseb | Code testing | GitHub | Day after day | Ferhat Bal

## Slide 9: Communication Plan
Stakeholder Analysis
Role Project | Project Sponsor Software Engineer Management team member | Project Sponsor Project Manager Hardware Specialist Smart contract developer | Project Sponsor Quality Assurance team Management team member
Organization | AZFCO. | AZFCO. | AZFCO.
Contact Information | Zaidmoh@protonmail.com | Jawabreh@protonmail.com | Ferhatbal@protonmail.com
Unique Facts | Prefers use GitHub for project code | Prefers use of email for project documents | Prefers use GitHub for project code and test sheets
Level of Interest | High | High | High
Level of Influence | High | High | High
Suggestions for managing relationships | Keep informed of all project progress | Keep informed of all project progress | Keep informed of all project progress

## Slide 10: Cont.
Project Reports
 | Data Needed | Frequency of Collection | Responsible Party for Data Collection & Analysis | Report Media & Format | Responsible Party for Distributing Report
Schedule Status | Tracking Gantt Chart | Weekly | Ahmad Jawabreh | Status Form | Ahmad Jawabreh
Work Progress | Tracking weakly achievements | Weekly | Zaid Mohtaseb | Work Progress form | Zaid Mohtaseb
Software quality audit | System code | Weekly | Ferhat Bal | Software quality form | Ferhat Bal

## Slide 11: Cont.
Project Information Accessibility
According to our company aims, there will be no centralize storing of the data all of our documentations and data will be storing using file chain protocol (file coin protocol), which give us a protocol to use thousands of distributed nodes around the world to store our data encrypted and distributed.

## Slide 12: Contract Agreement
Incentives:
The customer will pay more 10% if the system done within 75% of contracted period
The customer will pay more 25% if the system done within 50% of contracted period
Penalty
There will be 14 days grace period, and the seller will pay 3.5% for each day, and after that the seller will be forced to submit the product working correctly and fully evaluated with pass testing percentage.
Contract Closure
If the product quality does not meet the standards
If the work on the product finished after the grace period

## Slide 13: Contract management plan
Purpose of the contract:
To guarantee the right of both parties.
Determine the project delivery date.
Determining the total cost of the project and the quality and prices of the parts used in the project in detail.
Determine the evaluation method of the system.
Specify the work required.
Specify the incentives.
Specify the penalty and grace period.
Specify the payment method and the installments.

## Slide 14: Cont.
Pricing:
Total value of the contract is 1500 USD.
Installment:
25% Before starting work
25% After finishing the masked face recognition system and the alternative authentication method (RFID).
25% After finishing the smart contract work.
25% After finishing the system at all.
Incentive arrangements:
The customer will pay more 10% if the system done within 75% of contracted period.
The customer will pay more 25% if the system done within 50% of contracted period.

## Slide 15: Cont.
Contract Conditions:
The customer and the company will using simple smart contract designed and audited by trusted company (CertiK), the customer will pay the installments on the time directly to the smart contract, and after meeting the smart contract conditions the contract will convert the money directly to the company, If the company dose not meet the conditions the smart contract will return the money to the customer.

## Slide 16: Control Chart

## Slide 17: Corrective Actions List
No. | Issues Description | Description of Corrective Action | Assigned To | Target Date | Status | Metrics
1 | Make the hardware parts order and missing to order some parts | Contacting with the supplier and dealing to send the missing parts correctly | Zaid Motasib | 22/04/2022 | Completed | Supplier sent the parts quickly
2 | Very slow truffle environment | Contacting to Eng. Kostis Karantias in chainlink labs | Ahmad Jawabreh | 28/04/2021 | Completed | Sending the solution by chainlink labs
3 | Hardware parts stuck in the airport customs | Contacting with the airport customs department and solve the issue | Ferhat Bal | 11/05/2022 | Completed | finishing the customs clearance quickly

## Slide 18: Risk breakdown structure
1. Understand how the system algorithm exactly working.
1.1. Break the face analyzing algorithm
1.1.1. Hide face feature that is important for the system
2. If the system will be used as (God eye) there is a risk to give wrong reports.
2.1. Give report to arrest peoples by wrong.
3. Breaking chainlink bridge.
3.1. Steal the user’s information that cross the bridge.